## Sheet1
Table
Name | Area | Feature | Progress (%) | Cost (Days) | Description
Alex | Spelling bee game | draging sprites | 100 | 2 | Allows the letter tiles to be moved
Gabriel | Spelling bee game | Timer | 100 | 1 | Displays 10 second timer
Gabriel | Spelling bee game | Background | 100 | 2 | Made background from sprite package
Ben | Spelling bee game | Imported all words | 100 | 1 | Imported 3 to 6 letter words into the game
Ben | Spelling bee game | Set the word to solve | 100 | 1 | Set a new random word to be solved every time the game is launched
Ben | Sprite | Sprite for the tiles and letters | 100 | 1 | Added a rounded orange square for the letter tiles
Ben | Spelling bee game | Dragging | 100 | 2 | Allows the tiles to be dragged around only from left to right
Gabriel | Spelling bee game | Main menu | 100 | 2 | Made main menu with play, settings, help, and leaderboard buttons
Alex | Work Break Down Structure | Data Collection | 100 | 3 | Automated forms responses so we don't have to open excel to update WBS
Ben | Wordle | Basic Features of the Game | 100 | 1 | Create 5 letter Wordle, works just like the original
Ben | Wordle | List of possible words and guesses | 100 | 1 | Imported and created text files for a list of thousands of 6 and 7 letter words
Ben | Wordle | Increased word length to 7 | 100 | 1 | Made the original 5 letter Wordle to 7 letters to increase difficulty.
Ben | Wordle | Statistics UI | 100 | 1 | Created the basic UI for the statistics screen after solving the Wordle game.
Alex | Hosting | Website | 100% | 1 | Set up the webpage to begin making the game hosting & the designing of the site
Alex | Hosting | Embeded Game | 50% | 3 | Exported the build of a test to attempt to host a game with iframes that are now in the webpage.
Alex | Website | pages | 100% | 1 | added games page
Alex | Website | Pages | 100% | 1 | added about team page
Ben | Wordle | Words | 100 | 1 | Imported and edited list of thousands of 8 letter words
Ben | Wordle | Levels | 100 | 1 | Added an additional level with 8 letter words
Ben | Wordle | Levels | 100 | 2 | Added each level into its own scene
Ben | Wordle | Pause Menu UI | 100 | 1 | Added a pause menu UI
Ben | Leaderboards | Wordle Leaderboard UI | 100 | 1 | Created a leaderboard UI and script for handling scores in Wordle
Ben | Leaderboards | Scoring | 100 | 2 | Integrated Wordle scores into the leaderboard and into Unity, scores are now saved and can be submitted to leaderboard.
Ben | Accounts | Authentication Manager | 100 | 2 | Added a sign in and sign up feature where players can make accounts so their scores can be saved
Ben | Accounts | Anonymous Accounts | 100 | 1 | Allows players to play with anonymous accounts without having to make an account
Ben | Bugs | UI Fixes | 100 | 1 | Fixed bugs and fixes within the Wordle UI, leaderboard, and play sign in
Ben | Dino Game | Dino Game UI | 100 | 1 | Imported sprites and created UI and game scene for Dino Game
Ben | Dino Game | Finished Game | 100 | 2 | Finished the Dino Game, dinosaur jumps over obstacles and difficulty increases over time.
Ben | Leaderboards | Dino Game Leaderboard | 100 | 1 | Created the basic UI and scene for Dino Game Leaderboard
Ben | Menus | Main Menu | 30 | 1 | Created a scene for the main menu and added Wordle and Dino Game to the menu.
Ben | Scenes | Scenes Manager | 100 | 2 | Added all menus and scenes to the build settings and scenes manager to navigate through each game and scene.
Gabriel | Spelling bee game | Guessing | 100 | 1 | Get user's guess and store it in variable
Gabriel | Spelling bee game | Guessing | 100 | 1 | Displays user's guess in a text
Gabriel | Spelling bee game | Word Recognition | 100 | 1 | Compares guess to actual word assuming guess has the right amount of letters for that round
Gabriel | Spelling bee game | Levels | 100 | 1 | Moves user to next word after guessing correctly
Alex | Website | Website hosting | 100 | 1 | updated website with game that needs to be unblocked